## Sheet1
Business Analyst Involvement |  | Project Life Cycle (Generic) |  | Waterfall Methodology | Systems Analysis and Design |  |  | Project Management |  | System Development Life Cycle | PRINCE 2
(BABOK) |  |  |  |  | (Kendall and Kendall) |  |  | Fundamentals of Project Management (alison.com)
High |  | Enterprise/Problem Analysis | Analyse high-level needs and issues of the enterprise |  |  |  |  | Investigation | Commissioning of project | PLANNING: recognising and defining the problem; setting project objectives; identifying constraints; conducting feasibility studies; creating project proposals; establishing control mechanisms | PRE-PROJECT: Corporate Management provides project mandate; the trigger to start the Project
|  |  | Evaluate potential business initiatives | [5 empty] | Identification of initial aim and goals |  | Project mandate can be in different formats but could contain: main objective for the Project; business case; project scope; customers' quality epectations; customer info; other relevant info
| Business case(s) developed |  | Envision potential future state |  | Project identification and selection | Intelligence |  |  | Investigation of different ways to complete the project |  | STARTING UP A PROJECT: design and appoint the Project Management Team; create the Project Brief (including an outline of the Business Case); produce Initiation Stage Plan
High |  | Detailed Requirements Development | Elicit specific stakeholder wants and needs | Requirements | Project initiation and planning |  |  |  | Output is the project brief | ANALYSIS: existing system(s) are studied (strengths and weaknesses); data gathered and decisions made about how to proceed | INITIATION STAGE: prepare various documentation, such as Project Initiation Document, Business Case, Project Plan; define communications and other strategies; request permission to deliver the Project
|  |  | Document and prioritise stakeholder requirements |  | Analysis |  | Design | Planning and Design | Defining exact purpose and objectives for project
Medium |  | Design, Develop and Test | Translate requirements into solution components | Design | Logical design | Implementation |  |  | Identifying and defining activities/tasks | DESIGN: alternatives are investigated to ensure that the most efficient and effective solution is adopted; the new system is designed | VARIOUS DELIVERY STAGES: often aligned with natural review and decision points; managed, controlled, monitored and communicated, according to PRINCE 2 principles
|  |  | Design solution | [5 empty] | Determining resources, people, materials, equipment, costs, timings
|  |  | Validate requirements |  | Physical design |  |  |  | Outputs such as project plan, GANTT chart, PERT or network diagram
Low /Medium |  | Implementation | Implement solution | Implementation | Implementation |  |  | Production | Putting the plan into operation | IMPLEMENTATION: physical and conceptual resources are installed and integrated; educating users; changeover to new system | CLOSING A PROJECT: confirm products are delivered and accepted; handover products; capture lessons learned; review benefits; ensure product support after Project; evaluate the Project; prepare information for management and submit appropriate documentation; premature closure is an option if Project does not proceed as expected
|  |  |  | Verification |  |  |  |  | Meeting milestones and goals
Low |  | Maintenance /Support | Close project | Maintenance | Maintenance |  |  | Monitoring and Evaluation | Hand over completed project to clients | USE/EVALUATION: using, auditing and maintaining the system; proposals for re-engineering and change; appropriate data gathering using criteria such as efficiency, effectiveness and maintainability
|  |  | Provide ongoing solution support | [5 empty] | Implementation
Warranty
|  |  | Knowledge transfer | [5 empty] | Assessment based on elements of efficiency and effectiveness